## Sheet1
Timeline | Sprint Goals | Assigned Tasks | Priorities/Deliverables | Delivery Dates
week 9 17/04/2020 - 24/04/2020 | preparing for unity testing + finalising wiki info | mocking up combat environment tech art + unity + npc designs mock up opening menu (fancy buttons etc) same as last week finalising documentation | Design Wiki | 27/4/2020
week 10 24/04/2020 - 01/05/2020 | uploading documentation to wiki | uploading documentation to wiki initiate art repository on github | Design Wiki and playtest preperation | 2020-08-05
week 11 02/05/2020 - 08/05/2020 | Get a character in unity platforming scene ready to go | compiling assets into unity | First Playtest | 15/5/2020
week 12 09/05/2020 - 15/05/2020 | Preparing vertical slice, playtest questionnaires | Vertical slice Playtest questionnaire | Questionnaires phase 1 collection | 22/05/2020
week 13 16/05/2020 - 22/05/2020 | Analyse repsonses and begin demo refinement Combat system | Compile data from questionnaire responses Refine combat/combat icons | Questionnaire analysis game backgrounds and refined combat system | 26/05/2020 24/05/2020
week 14 23/05/2020 - 29/05/2020 | Movement/animation | Animation Movement coding | Refined character movement | 30/06/2020
week 15 30/05/2020 - 5/06/2020 | Complete written components and deliver game | Deliver project in its final state | Project report Completed project | 2020-05-06