## Sheet1
Timeline | Sprint Goals | Assigned Tasks | Priorities/Deliverables | Delivery Dates
week 4 17/08/2020 - 23/08/2020 | basic animations finished platforms and environment assets character/expression/pose sheets | animation - natalie clean up - hayley/rhys character enemy design - rhys environment art - dana/hayley unity - cameron | Rough animation Dash and Idle Clean up animation Hover and Walk Platformss and landscapes blog post | week 5
week 5 - BREAK WEEK 24/08/2020 - 30/08/2020 | Finalising animations - redo jump, attacks, take hit, dash, die Background finalisation Implement movement with animations in unity NPC/enemy design UI design | animation - natalie clean up - hayley/rhys character enemy design - rhys environment art - dana/hayley unity - cameron | Attack, jump, take hit, dash, die animations backgrounds and layouts blog post | week 6
week 6 31/08/2020 - 06/09/2020 | Sound effects Environment assets finished marketing and advertising*/Merch and website research enemy animation tutorial level Intro cutscene storyboarding | Sound - rhys environment assets - dana and hayley unity animation finalisation - cameron animation clean up - hayley | environment assets animation clean up animation in unity blog post | week 7
week 7 07/09/2020 - 13/09/2020 | *development marketing/advertising second level enemy animation finalise UI implementation | animation - natalie UI function - cameron UI design - dana and hayley marketing/sound - rhys | enemy animation UI marketing + merch ideas blog post | week 8
week 8 14/09/2020 - 20/09/2020 | enemy animation clean up finalise UI finalise Combat functional Enemy implementation | combat - cameron UI and asset design - dana and hayley animation - natalie marketing/sound - rhys | Combat final asset designs blog post | week 9
week 9 21/09/2020 - 27/09/2020 | Enemy integration into levels UI complete + functional First Playtest marketing mockup designs | marketing/sound - rhys unity functionality - cameron marketing and merch design - dana and hayley | Playtest for following week w/ feedback survey marketing mockups blog post | week 10
week 10 - BREAK WEEK 28/09/2020 - 04/10/2020 | MARKETING Sound finalising Playtest Ready Designing booth - decor, merch planning | marketing/sound - rhys unity functionality - cameron marketing and merch design - dana and hayley | Playtest + surveys Sound + music blog post | week 11
week 11 05/10/2020 - 11/10/2020 | Polishing plan written component Special effects Marketing - poster second pass Marketing - trailer first pass (promo) | marketing/sound - rhys unity functionality - cameron marketing and merch design - dana and hayley | Poster and booth designs Teaser trailer v1 Bug fixes blog post | week 12
week 12 12/10/2020 - 18/10/2020 | Playtesting and final polish Marketing - Finalise Poster and trailer second pass End of semester build/release | marketing/sound - rhys unity functionality - cameron marketing and merch design - dana and hayley | Poster and booth designs Teaser trailer + steam page ideas Bug fixes blog post | week 13
week 13 19/10/2020 - 25/10/2020 | Marketing - Trailer finalise, team website mock steam page Marketing - booth and merch final polish and bug fixing | marketing/sound - rhys unity functionality - cameron marketing and merch design - dana and hayley | Merchandise Steam page mockup website blog post | week 14
week 14 26/10/2020 - 01/11/2020 | Complete and deliver Written Component polish and bug fixing | Written Component - All team members marketing/sound - rhys unity functionality - cameron marketing and merch design - dana and hayley | Marketing + merch bug fixes Written Component | week 15 30/10/2020
week 15 02/11/2020 - 08/11/2020 | polish and bug fixing for showcase Feedback |  |  | showcase (tbd)